## Sheet1
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
1. Successfully integrated NPK, pH, and moisture sensors with Raspberry Pi. | 1. Inconsistent data readings from sensors, potentially due to calibration issues or environmental interference. | 1. Implement a sensor calibration routine during startup and at regular intervals. | 1. Research effective calibration methods for each sensor type and create a script to automate the process. | Guidelines: Use NIST-traceable standards, consider sensor-specific environmental factors, and document all calibration procedures thoroughly.
2. Established basic MongoDB connection and data insertion for sensor readings. | 2. Image capture from RTSP stream was unreliable and prone to failure, affecting data completeness. | 2. Explore alternative camera libraries (e.g., picamera) or streaming protocols for more robust image capture. | 2. Experiment with different streaming parameters (e.g., resolution, frame rate) to optimize stability. | Guidelines: Evaluate library performance, test in various network conditions, and set buffer parameters to avoid overload.
3. Developed initial code structure for reading and processing sensor data. | 3. Code lacked comprehensive error handling, leading to potential program crashes and data loss. | 3. Incorporate exception handling blocks for each sensor reading and data processing function. | 3. Conduct thorough code reviews with a focus on robustness and error prevention. | Guidelines: Follow defensive programming principles, implement try-except blocks, and log errors for debugging purposes.
4.The team demonstrated good collaboration and communication. Real-time data processing with 5 seconds latency between collection cycles | 4.Add a Proper real-time environment | 4. Implement the raspberry pi cron job for proper data collection cycle | 4.Implement cron job and test for proper collection of the real-time parameters | Guidelines: Use proper sensors which are efficient high range with the minimum time cycle.